## Tasks
ID | Task | Detail | Owner | Deadline | Status | Depends on | Notes
T01 | Label CS workbook | annotator_4_CS_majors.xlsx — 413 rows (60 overlap + 293 training + 60 test) | Team | Sat 03 Oct | Not started |  | Overlap 60 must be labelled independently, no discussion, or kappa is void
T02 | Label psych workbooks | annotator_1 Laiba 421 / annotator_2 Reesha 418 / annotator_3 Hurema 415 rows | Laiba | Sat 03 Oct | Not started |  | ~5h 10m each at 45 s/row; unfinished rows are acceptable
T03 | Merge labels + agreement | Run scripts/relabel_agreement.py on returned workbooks | Nayab | Sun 04 Oct | Not started | T01, T02 | Produces merged_labels.csv, agreement_report.md, unsure_for_adjudication.csv
T04 | Adjudicate Unsure rows | Psych annotators resolve rows flagged Unsure | Laiba | Tue 06 Oct | Not started | T03 | Nobody owned this before; needed before the labels are final
T05 | Separate errors from redefinitions | Split label changes into genuine errors vs calibrated-pessimism redefinition | Nayab | Tue 06 Oct | Not started | T03 | Original annotation had no justified-concern rule; keep the two countable apart
T06 | Back-translation augmentation | Inflate under-represented classes in the relabelled train split | Lumia | Thu 08 Oct | Not started | T03, T04 | TRAIN ONLY. Augmented rows stay in their source row's split or it is leakage
T07 | Decide span handling for augmented rows | Back-translation breaks 'Distorted part' offsets | Lumia | Wed 07 Oct | Not started | T06 | Either re-translate + re-locate the span, or mark rows classification-only
T08 | Hand-check augmented samples | 30 rows per augmented class: did the distortion cue survive? | Izza | Fri 09 Oct | Not started | T06 | 'I'll never get funding' -> 'I might not' is no longer fortune-telling
T09 | CBT-Bench: acquire + map labels | Psychotherapy-LLM/CBT-Bench on HuggingFace; CBT-CD split, 146 items, 10 classes | Izza | Wed 30 Sep | Not started |  | Write an explicit label mapping; record how many items had to be dropped
T10 | Evaluate fine-tuned model on CBT-Bench | Transfer test of the TherapistQA-trained model | Izza | Fri 02 Oct | Not started | T09 | Only 146 items (~15/class): report support counts, no headline single number
T11 | Span approach: literature + decision | BIO token tagging vs sentence classification vs extractive QA | Nayab | Wed 30 Sep | Not started |  | Recommendation: sentence-level — annotators flagged sentences, report promises it
T12 | Build sentence labels from spans | Split into sentences; label the one containing the gold span; use find_span offsets | Nayab | Fri 02 Oct | Not started | T11 | Current span_crop/span_marked modes are ORACLE; the selector does not exist yet
T13 | Train + evaluate span selector | Sentence accuracy and span overlap, reported separately from classification | Nayab | Thu 08 Oct | Not started | T12 | Report the 0.402 oracle as an upper bound and the selector's cost as the gap
T14 | Hyperparameter tuning | LR (2e-5/3e-5/5e-5), epochs, max_length, weight decay on the original dataset | Lumia | Fri 02 Oct | Not started |  | Val only. Confirm the winner across all 3 seeds; single-seed wins are noise
T15 | Over/underfitting diagnosis | Train vs val loss curves per epoch; early stop on val macro-F1 | Lumia | Fri 02 Oct | Not started | T14 | ~2,000 train rows: expect overfitting from epoch 3-4
T16 | Decide target dataset sizes | How many seed + test items the entrepreneurial set needs | Nayab | Tue 29 Sep | Not started |  | ~100 non-distorted for +/-10% specificity CI; ~20/class -> 200-300 for per-class
T17 | Scraping: sources + ToS check | Pick sources, confirm terms of service and redistribution limits | Izza | Wed 30 Sep | Not started | T16 | Scraped text can be republished only as derived data in most cases
T18 | Scrape entrepreneurial text | Volume set by T16; cleaning and de-duplication included | Izza | Sat 03 Oct | Not started | T17 | Unlabelled at this stage; labels come later with Laiba
T19 | Circulate form + start thread | Post to relevant entrepreneurial groups/sites; collect responses | Lumia | Wed 30 Sep | Not started |  | Consent + anonymisation first. Responses are EVALUATION ONLY, never prompts
T20 | Triage form responses | Keep responses usable for the entrepreneurial set | Lumia | Sat 03 Oct | Not started | T19 | Held out at natural class distribution; do not balance
T21 | Compile entrepreneurial dataset (unlabelled) | Merge scraped + form text into one schema, ready for labelling | Team | Sat 03 Oct | Not started | T18, T20 | WEEK GOAL. Labels follow later with Laiba and the team
T22 | Seed the justified-concern set | Harvest calibrated-pessimism rows from the relabelling output | Nayab | Mon 05 Oct | Not started | T03 | Real, human-verified justified concerns; clinical topic, entrepreneurial rewrite needed
T23 | Write challenge-set pairs | 20 matched justified/distorted pairs per distortion family | Team | Fri 09 Oct | Not started | T22 | Matched pairs give controls for free and block style shortcuts
T24 | Style-leak check on challenge set | TF-IDF + logistic regression must score near chance on justified vs distorted | Nayab | Sat 10 Oct | Not started | T23 | If it separates them easily (>0.75 F1) the set leaks surface cues — rewrite

## Notes
Week of Mon 28 Sep 2026 — deadline for the compiled dataset: Sat 03 Oct
Status values | Not started, In progress, Blocked, Done
Row colour | amber = in progress, red = blocked, green = done
Standing rules
1 | Augmentation is TRAIN ONLY; never val or test.
2 | Augmented rows stay in their source row's split, or it is leakage.
3 | Form/interview responses are EVALUATION ONLY — never prompts, never training.
4 | The test set is never balanced; it stays at its natural distribution.
5 | Thresholds are tuned on val. Test is read once, at the end.
6 | The challenge set is evaluation only and is frozen once verified.